## Client master tracker
Client master tracker
Track active clients, status, owner, next action, renewal date and risk level.
Active clients |  | In onboarding |  | High risk |  |  | Renewals in 30 days
10 |  | 4 |  | 3 |  |  | 5
How to use
1. Add one row per client. Replace the sample rows. 2. Update the status, next action and risk level at least once a week. 3. Days to renewal is calculated. Do not type over it. 4. Review all rows marked high risk in your weekly delivery meeting.
Client name | Status | Owner | Next action | Next action date | Renewal date | Days to renewal | Risk level | Notes
Northwind Coffee Co. | Active | Sarah Chen | Present product page templates | 2026-10-20 | 2027-03-31 | 169 | Low | Retainer client since 2024. Website redesign and holiday campaign running.
Brightline Dental | Active | Marcus Webb | Chase landing page sign-off and booking API access | 2026-10-14 | 2026-11-05 | 23 | Medium | Renewal due soon. Landing page is past deadline while we wait on API access.
Halcyon Fitness | Active | Priya Nair | Escalation call on scope and round limits | 2026-10-15 | 2026-10-30 | 17 | High | Onboarding UI is overdue and revisions are over the agreed limit. Renewal at risk.
Verdant Home Goods | Onboarding | Tom Alvarez | Collect product list and SKUs | 2026-10-20 | 2027-09-30 | 352 | Low | New client, signed September 2026. Shopify store build started.
Kestrel Legal LLP | Active | Sarah Chen | Get whitepaper sign-off | 2026-10-15 | 2027-01-15 | 94 | Medium | Content retainer. Approvals can be slow because of partner review.
Oakridge Veterinary | Paused | Marcus Webb | Check-in call to confirm restart date | 2026-10-21 | 2026-12-01 | 49 | High | Website project paused by the client in September. Still waiting on the services list.
Lumen Solar | Onboarding | Priya Nair | Review brand questionnaire answers | 2026-10-16 | 2027-10-01 | 353 | Medium | New client. Brand identity kickoff held 5 October.
Pinecrest Bakery | Offboarding | Tom Alvarez | Deliver asset handover pack | 2026-10-28 | 2026-10-31 | 18 | Low | Not renewing (moving in-house). Ending on good terms.
Bluefin Seafood Market | Active | Marcus Webb | Chase payment gateway access | 2026-10-14 | 2027-05-31 | 230 | Low | Ordering site on track. Client replies quickly.
Summit Ridge Outfitters | Active | Tom Alvarez | Send round 2 catalogue edits | 2026-10-15 | 2026-11-10 | 28 | Medium | Catalogue is past deadline because product photos came in late. Renewal due soon.
Copperleaf Accounting | Active | Sarah Chen | Review email nurture drafts | 2026-10-22 | 2027-02-28 | 138 | Low | Happy client. Tax season campaign under way.
Meridian Physio | Onboarding | Priya Nair | Run website discovery workshop | 2026-10-19 | 2027-10-15 | 367 | Low | New client, signed October 2026.
Atlas Logistics | Active | Marcus Webb | Agree change request for extra deck work | 2026-10-14 | 2026-11-30 | 48 | High | Sales deck is overdue and the scope keeps growing. Slow to send data.
Willow & Thread Boutique | Active | Tom Alvarez | Share first lookbook spreads | 2026-10-23 | 2027-04-30 | 199 | Low | Long-standing client. Spring lookbook in production.
Greenleaf Architects | Paused | Sarah Chen | Follow up on photography rights | 2026-10-16 | 2027-01-31 | 110 | Medium | Portfolio site paused until photo rights are cleared.
Riverstone Brewing | Active | Priya Nair | Get final sign-off on label print files | 2026-10-15 | 2026-11-08 | 26 | Medium | Renewal due soon. Label designs approved. Print files in review.
Nova Pet Supplies | Onboarding | Marcus Webb | Brand launch kickoff | 2026-10-15 | 2027-10-20 | 372 | Low | New client. Brand launch kit planned for December.
Cedar Grove Hotel | Closed | Tom Alvarez | Send end-of-contract survey | 2026-10-20 | 2026-09-30 | -13 | Low | Contract ended 30 Sep 2026. Booking flow refresh delivered.
Formulas:
Days to renewal = IF([Renewal date]="","",[Renewal date]-TODAY())

## Project tracker
Project tracker
Track projects, deliverables, deadlines, owners and completion status.
In progress |  | Overdue |  |  | Due in 7 days |  |  |  | Complete
11 |  | 4 |  |  | 3 |  |  |  | 3
How to use
1. Add one row per project. Replace the sample rows. 2. Set the status, percent complete and next step at least once a week. 3. Days overdue and the deadline flag are calculated. Do not type over them. 4. Review every project flagged Overdue in your weekly delivery meeting.
Project name | Client name | Owner | Deliverables | Start date | Deadline | Status | Percent complete | Days overdue | Deadline flag | Next step
Northwind website redesign | Northwind Coffee Co. | Sarah Chen | Homepage, product page templates, CMS build | 2026-07-01 | 2026-11-20 | In progress | 65 | 0 | On track | Present product page templates on 20 Oct
Northwind holiday campaign | Northwind Coffee Co. | Sarah Chen | Holiday social ad set, holiday email series | 2026-09-15 | 2026-10-18 | In progress | 50 | 0 | Due soon | Finish round 2 ad edits and quote TikTok sizes
Brightline brand refresh | Brightline Dental | Marcus Webb | Logo suite, brand guidelines | 2026-06-01 | 2026-09-30 | Complete | 100
Brightline booking landing page | Brightline Dental | Marcus Webb | Booking landing page | 2026-09-01 | 2026-10-10 | In review | 90 | 3 | Overdue | Chase sign-off and booking API credentials
Halcyon app onboarding flow | Halcyon Fitness | Priya Nair | Onboarding UX wireframes, onboarding UI designs | 2026-08-01 | 2026-10-03 | In progress | 70 | 10 | Overdue | Agree change request for extra screens
Halcyon January membership campaign | Halcyon Fitness | Priya Nair | Campaign concept | 2026-10-20 | 2026-12-15 | Not started | 0 | 0 | On track | Confirm January pricing before kickoff
Verdant Shopify store launch | Verdant Home Goods | Tom Alvarez | Store theme design, product photography | 2026-10-01 | 2026-12-12 | In progress | 15 | 0 | On track | Start theme design once SKUs arrive
Kestrel thought leadership content | Kestrel Legal LLP | Sarah Chen | Whitepaper, blog articles (x4) | 2026-08-15 | 2026-10-17 | In review | 85 | 0 | Due soon | Apply section 3 edits and get partner sign-off
Oakridge website refresh | Oakridge Veterinary | Marcus Webb | Website page designs | 2026-07-15 | 2026-11-30 | On hold | 40 | 0 | On track | Paused by client. Confirm restart date
Lumen Solar brand identity | Lumen Solar | Priya Nair | Logo concepts | 2026-10-05 | 2027-01-29 | In progress | 10 | 0 | On track | Finish logo concepts for 6 Nov
Pinecrest menu and signage | Pinecrest Bakery | Tom Alvarez | Menu design, store signage | 2026-08-01 | 2026-09-26 | Complete | 100
Pinecrest handover pack | Pinecrest Bakery | Tom Alvarez | Asset handover pack | 2026-10-05 | 2026-10-28 | In progress | 30 | 0 | On track | Package final files and brand assets
Bluefin online ordering site | Bluefin Seafood Market | Marcus Webb | Ordering site design, menu photography | 2026-08-10 | 2026-10-30 | In progress | 75 | 0 | On track | Get payment gateway access
Summit Ridge winter catalogue | Summit Ridge Outfitters | Tom Alvarez | Winter catalogue | 2026-08-20 | 2026-10-11 | In progress | 80 | 2 | Overdue | Finish round 2 edits and get catalogue sign-off
Copperleaf tax season campaign | Copperleaf Accounting | Sarah Chen | Email nurture series, LinkedIn ads | 2026-10-01 | 2026-12-05 | In progress | 20 | 0 | On track | Draft nurture emails 1 to 3
Meridian Physio website build | Meridian Physio | Priya Nair | Sitemap and wireframes, website design | 2026-10-19 | 2027-01-22 | Not started | 0 | 0 | On track | Discovery workshop on 19 Oct
Atlas Logistics sales deck | Atlas Logistics | Marcus Webb | Sales deck, case study one-pagers | 2026-08-15 | 2026-09-30 | In review | 85 | 13 | Overdue | Send change request for French version
Willow & Thread spring lookbook | Willow & Thread Boutique | Tom Alvarez | Lookbook design, social teasers | 2026-09-28 | 2026-11-27 | In progress | 35 | 0 | On track | Lay out first 12 spreads
Greenleaf portfolio site | Greenleaf Architects | Sarah Chen | Portfolio site design | 2026-07-20 | 2026-11-15 | On hold | 45 | 0 | On track | Waiting on photography rights
Riverstone label redesign | Riverstone Brewing | Priya Nair | Can label designs, label print files | 2026-08-25 | 2026-10-19 | In review | 90 | 0 | Due soon | Final print file check with printer
Nova Pet brand launch kit | Nova Pet Supplies | Marcus Webb | Brand launch kit | 2026-10-08 | 2026-12-18 | In progress | 5 | 0 | On track | Kickoff and mood boards
Cedar Grove booking flow refresh | Cedar Grove Hotel | Tom Alvarez | Booking flow redesign | 2026-06-01 | 2026-08-29 | Complete | 100
Formulas:
Days overdue = IF(OR([Due in 7 days]="",[Status]="Complete"),"",MAX(0,TODAY()-[Due in 7 days]))
Complete = IF(OR([Due in 7 days]="",[Status]="Complete"),"",IF([Due in 7 days]<TODAY(),"Overdue",IF([Due in 7 days]-TODAY()<=7,"Due soon","On track")))

## Deliverable tracker
Deliverable tracker
Track each deliverable from brief to approval.
Open deliverables |  | Overdue |  |  |  | Waiting on client |  |  | Approved
21 |  | 4 |  |  |  | 3 |  |  | 9
How to use
1. Add one row per deliverable. Replace the sample rows. 2. Move the stage forward as the work progresses, from Brief to Approved. 3. Enter the due date and the date approved. Days overdue and the stage flag are calculated. 4. Review every row flagged Overdue or Waiting on client in your weekly delivery meeting.
Deliverable | Project name | Client name | Owner | Stage | Due date | Date sent to client | Date approved | Approver | Days overdue | Stage flag | Notes
Homepage design | Northwind website redesign | Northwind Coffee Co. | Sarah Chen | Approved | 2026-09-12 | 2026-09-08 | 2026-09-11 | Emma Larsen |  | Done | Approved after one round
Product page templates | Northwind website redesign | Northwind Coffee Co. | Sarah Chen | Sent to client | 2026-10-20 | 2026-10-09 |  | Emma Larsen | 0 | Waiting on client | Size chart request in progress
CMS build | Northwind website redesign | Northwind Coffee Co. | Sarah Chen | In production | 2026-11-13 |  |  | Emma Larsen | 0 | On track | Needs full product catalogue CSV
Holiday social ad set | Northwind holiday campaign | Northwind Coffee Co. | Sarah Chen | Revisions | 2026-10-16 | 2026-10-06 |  | Emma Larsen | 0 | On track | Round 2 of 2. Extra TikTok sizes quoted
Holiday email series | Northwind holiday campaign | Northwind Coffee Co. | Sarah Chen | Internal review | 2026-10-17 |  |  | Emma Larsen | 0 | On track
Logo suite | Brightline brand refresh | Brightline Dental | Marcus Webb | Approved | 2026-08-15 | 2026-08-10 | 2026-08-14 | Dr. Raj Patel |  | Done
Brand guidelines | Brightline brand refresh | Brightline Dental | Marcus Webb | Approved | 2026-09-25 | 2026-09-18 | 2026-09-24 | Dr. Raj Patel |  | Done | Brand blue darkened for accessibility
Booking landing page | Brightline booking landing page | Brightline Dental | Marcus Webb | Sent to client | 2026-10-10 | 2026-10-07 |  | Dr. Raj Patel | 3 | Overdue | Blocked by booking API credentials
Onboarding UX wireframes | Halcyon app onboarding flow | Halcyon Fitness | Priya Nair | Approved | 2026-09-05 | 2026-09-02 | 2026-09-09 | Jordan Blake |  | Done
Onboarding UI designs | Halcyon app onboarding flow | Halcyon Fitness | Priya Nair | Revisions | 2026-10-03 | 2026-09-29 |  | Jordan Blake | 10 | Overdue | Round 4 requested. Over the 2 included rounds
Campaign concept | Halcyon January membership campaign | Halcyon Fitness | Priya Nair | Brief | 2026-11-06 |  |  | Jordan Blake | 0 | On track | Waiting on January pricing
Store theme design | Verdant Shopify store launch | Verdant Home Goods | Tom Alvarez | In production | 2026-11-14 |  |  | Mia Fontaine | 0 | On track
Product photography | Verdant Shopify store launch | Verdant Home Goods | Tom Alvarez | Brief | 2026-11-21 |  |  | Mia Fontaine | 0 | On track | Shoot list depends on SKU list
Whitepaper | Kestrel thought leadership content | Kestrel Legal LLP | Sarah Chen | Sent to client | 2026-10-17 | 2026-10-08 |  | Oliver Grant | 0 | Waiting on client | Partner review in progress
Blog articles (x4) | Kestrel thought leadership content | Kestrel Legal LLP | Sarah Chen | Approved | 2026-09-30 | 2026-09-22 | 2026-09-29 | Oliver Grant |  | Done
Website page designs | Oakridge website refresh | Oakridge Veterinary | Marcus Webb | Internal review | 2026-11-20 |  |  | Dr. Hannah Cole | 0 | On track | Paused with the project
Logo concepts | Lumen Solar brand identity | Lumen Solar | Priya Nair | In production | 2026-11-06 |  |  | Daniel Okafor | 0 | On track
Menu design | Pinecrest menu and signage | Pinecrest Bakery | Tom Alvarez | Approved | 2026-09-12 | 2026-09-07 | 2026-09-10 | Rosa Martinez |  | Done
Store signage | Pinecrest menu and signage | Pinecrest Bakery | Tom Alvarez | Approved | 2026-09-26 | 2026-09-21 | 2026-09-25 | Rosa Martinez |  | Done
Asset handover pack | Pinecrest handover pack | Pinecrest Bakery | Tom Alvarez | In production | 2026-10-28 |  |  | Rosa Martinez | 0 | On track | Final deliverable before offboarding
Ordering site design | Bluefin online ordering site | Bluefin Seafood Market | Marcus Webb | Sent to client | 2026-10-16 | 2026-10-09 |  | Kai Thompson | 0 | Waiting on client | Allergen filter request in progress
Winter catalogue | Summit Ridge winter catalogue | Summit Ridge Outfitters | Tom Alvarez | Revisions | 2026-10-11 | 2026-10-02 |  | Lena Brooks | 2 | Overdue | Round 2 of 2
Email nurture series | Copperleaf tax season campaign | Copperleaf Accounting | Sarah Chen | In production | 2026-11-06 |  |  | Greg Holloway | 0 | On track
Sitemap and wireframes | Meridian Physio website build | Meridian Physio | Priya Nair | Brief | 2026-11-13 |  |  | Aisha Rahman | 0 | On track | Starts after discovery workshop
Sales deck | Atlas Logistics sales deck | Atlas Logistics | Marcus Webb | Sent to client | 2026-09-30 | 2026-09-26 |  | Victor Ramos | 13 | Overdue | Round 3 requested. Over the limit
Case study one-pagers | Atlas Logistics sales deck | Atlas Logistics | Marcus Webb | Internal review | 2026-10-23 |  |  | Victor Ramos | 0 | On track | Waiting on shipment data
Lookbook design | Willow & Thread spring lookbook | Willow & Thread Boutique | Tom Alvarez | In production | 2026-11-13 |  |  | Chloe Bennett | 0 | On track
Portfolio site design | Greenleaf portfolio site | Greenleaf Architects | Sarah Chen | Internal review | 2026-11-06 |  |  | Simon Hart | 0 | On track | Paused with the project
Can label designs | Riverstone label redesign | Riverstone Brewing | Priya Nair | Approved | 2026-10-09 | 2026-10-02 | 2026-10-08 | Ben Kowalski |  | Done | Approved after two rounds
Booking flow redesign | Cedar Grove booking flow refresh | Cedar Grove Hotel | Tom Alvarez | Approved | 2026-08-22 | 2026-08-15 | 2026-08-21 | Natalie Ross |  | Done
Formulas:
Approved = IF(OR([Due date]="",[Stage]="Approved"),"",MAX(0,TODAY()-[Due date]))
Stage flag = IF([Stage]="","",IF([Stage]="Approved","Done",IF(AND([Due date]<>"",[Due date]<TODAY()),"Overdue",IF([Stage]="Sent to client","Waiting on client","On track"))))

## Asset tracker
Asset tracker
Track missing client assets, access requests and outstanding items.
Open items |  | Chase now |  |  | Received |  |  |  | Longest wait in days
16 |  | 10 |  |  | 8 |  |  |  | 73
How to use
1. Add one row per item you need from the client, such as a file, a login invite or an answer. 2. Enter the date you requested it and the date you need it. Update the status when it arrives. 3. Days waiting and the chase flag are calculated. Do not type over them. 4. Send a reminder for every row flagged Chase now, and note the date in the last chased column.
Item needed | Type | Client name | Project name | Owner | Date requested | Needed by | Status | Last chased | Days waiting | Chase flag | Notes
Full product catalogue CSV | File | Northwind Coffee Co. | Northwind website redesign | Sarah Chen | 2026-09-20 | 2026-10-06 | Partly received | 2026-10-08 | 23 | Chase now | Half the range received. Needed for CMS build
Holiday product photos | File | Northwind Coffee Co. | Northwind holiday campaign | Sarah Chen | 2026-09-22 | 2026-10-01 | Received |  |  | Closed
Invite to Meta Ads Manager | Access request | Northwind Coffee Co. | Northwind holiday campaign | Sarah Chen | 2026-09-16 | 2026-09-25 | Received |  |  | Closed
Booking system API credentials | Access request | Brightline Dental | Brightline booking landing page | Marcus Webb | 2026-09-03 | 2026-09-20 | Reminder sent | 2026-10-06 | 40 | Chase now | Blocking landing page go-live
Booking landing page sign-off | Approval | Brightline Dental | Brightline booking landing page | Marcus Webb | 2026-10-07 | 2026-10-10 | Requested |  | 6 | Chase now | Ask Dr. Patel directly
App store screenshots | File | Halcyon Fitness | Halcyon app onboarding flow | Priya Nair | 2026-08-05 | 2026-08-20 | Reminder sent | 2026-10-01 | 69 | Chase now | Raise on escalation call
January membership pricing | Information | Halcyon Fitness | Halcyon January membership campaign | Priya Nair | 2026-10-02 | 2026-10-23 | Requested |  | 11 | Waiting
Shopify store admin invite | Access request | Verdant Home Goods | Verdant Shopify store launch | Tom Alvarez | 2026-10-01 | 2026-10-09 | Received |  |  | Closed
Product list and SKUs | File | Verdant Home Goods | Verdant Shopify store launch | Tom Alvarez | 2026-10-01 | 2026-10-20 | Requested |  | 12 | Waiting
Partner bios and headshots | File | Kestrel Legal LLP | Kestrel thought leadership content | Sarah Chen | 2026-08-20 | 2026-09-10 | Received |  |  | Closed
Whitepaper sign-off | Approval | Kestrel Legal LLP | Kestrel thought leadership content | Sarah Chen | 2026-10-08 | 2026-10-15 | Requested |  | 5 | Waiting
Updated veterinary services list | Information | Oakridge Veterinary | Oakridge website refresh | Marcus Webb | 2026-08-25 | 2026-09-15 | Reminder sent | 2026-09-29 | 49 | Chase now | Client paused project
Existing brand assets | File | Lumen Solar | Lumen Solar brand identity | Priya Nair | 2026-10-05 | 2026-10-12 | Received |  |  | Closed
Brand questionnaire | Information | Lumen Solar | Lumen Solar brand identity | Priya Nair | 2026-10-05 | 2026-10-14 | Partly received |  | 8 | Waiting | Values section still blank
Original logo files | File | Pinecrest Bakery | Pinecrest handover pack | Tom Alvarez | 2026-10-06 | 2026-10-20 | Not needed |  |  | Closed | We already hold the master files
Menu with prices | File | Bluefin Seafood Market | Bluefin online ordering site | Marcus Webb | 2026-09-15 | 2026-10-01 | Received |  |  | Closed
Payment gateway access | Access request | Bluefin Seafood Market | Bluefin online ordering site | Marcus Webb | 2026-10-01 | 2026-10-12 | Reminder sent | 2026-10-09 | 12 | Chase now | Needed before ordering site goes live
Winter product photos | File | Summit Ridge Outfitters | Summit Ridge winter catalogue | Tom Alvarez | 2026-08-25 | 2026-09-15 | Partly received | 2026-10-05 | 49 | Chase now | 8 of 14 products still missing
Winter catalogue sign-off | Approval | Summit Ridge Outfitters | Summit Ridge winter catalogue | Tom Alvarez | 2026-10-02 | 2026-10-09 | Requested |  | 11 | Chase now
Client testimonials | Information | Copperleaf Accounting | Copperleaf tax season campaign | Sarah Chen | 2026-10-05 | 2026-10-26 | Requested |  | 8 | Waiting
Domain registrar login | Access request | Meridian Physio | Meridian Physio website build | Priya Nair | 2026-10-12 | 2026-10-26 | Requested |  | 1 | Waiting
Shipment volume data for case studies | Information | Atlas Logistics | Atlas Logistics sales deck | Marcus Webb | 2026-08-20 | 2026-09-10 | Reminder sent | 2026-10-07 | 54 | Chase now | Blocking case study one-pagers
Spring collection product list | File | Willow & Thread Boutique | Willow & Thread spring lookbook | Tom Alvarez | 2026-09-29 | 2026-10-10 | Received |  |  | Closed
Project photography rights | Approval | Greenleaf Architects | Greenleaf portfolio site | Sarah Chen | 2026-08-01 | 2026-08-30 | Reminder sent | 2026-09-20 | 73 | Chase now | Reason the project is paused
Label printer die-line template | File | Riverstone Brewing | Riverstone label redesign | Priya Nair | 2026-08-28 | 2026-09-10 | Received |  |  | Closed
Formulas:
Longest wait in days = IF(OR([Received]="",[Status]="Received",[Status]="Not needed"),"",MAX(0,TODAY()-[Received]))
Chase flag = IF([Status]="","",IF(OR([Status]="Received",[Status]="Not needed"),"Closed",IF(AND([Needed by]<>"",[Needed by]<TODAY()),"Chase now","Waiting")))

## Revision tracker
Revision tracker
Track revision requests, scope status, resolution and approval.
Open requests |  | Over limit |  |  | New requirements |  |  |  | Awaiting approval
8 |  | 3 |  |  | 3 |  |  |  | 12
How to use
1. Add one row per revision request. Replace the sample rows. 2. Set the round number and scope status, then record the resolution and the approval date. 3. The round flag is calculated. A round above the number included in your scope is marked Over limit. 4. Review every row marked New requirement or Over limit before you start work on it.
Request | Deliverable | Project name | Client name | Date received | Round number | Rounds included | Round flag | Scope status | Resolution | Approval | Date approved | Owner
Swap hero image for seasonal photo | Homepage design | Northwind website redesign | Northwind Coffee Co. | 2026-09-09 | 1 | 2 | Within limit | In scope | Resolved | Approved | 2026-09-11 | Sarah Chen
Add size comparison chart to product template | Product page templates | Northwind website redesign | Northwind Coffee Co. | 2026-10-12 | 1 | 2 | Within limit | Reasonable revision | In progress | Pending |  | Sarah Chen
Change ad headline copy | Holiday social ad set | Northwind holiday campaign | Northwind Coffee Co. | 2026-10-08 | 1 | 2 | Within limit | In scope | Resolved | Pending |  | Sarah Chen
Add two extra ad sizes for TikTok | Holiday social ad set | Northwind holiday campaign | Northwind Coffee Co. | 2026-10-10 | 2 | 2 | Last round | New requirement | Quoted as extra | Pending |  | Sarah Chen
Darken brand blue for accessibility | Brand guidelines | Brightline brand refresh | Brightline Dental | 2026-09-19 | 1 | 3 | Within limit | Reasonable revision | Resolved | Approved | 2026-09-24 | Marcus Webb
Move booking form above the fold | Booking landing page | Brightline booking landing page | Brightline Dental | 2026-10-08 | 1 | 2 | Within limit | In scope | Resolved | Pending |  | Marcus Webb
Simplify sign-up to 3 steps | Onboarding UI designs | Halcyon app onboarding flow | Halcyon Fitness | 2026-09-30 | 2 | 2 | Last round | In scope | Resolved | Approved with changes | 2026-10-05 | Priya Nair
Add Apple Health integration screens | Onboarding UI designs | Halcyon app onboarding flow | Halcyon Fitness | 2026-10-06 | 3 | 2 | Over limit | Change request sent | Open | Pending |  | Priya Nair
Rework colour palette again | Onboarding UI designs | Halcyon app onboarding flow | Halcyon Fitness | 2026-10-09 | 4 | 2 | Over limit | Needs clarification | Open | Pending |  | Priya Nair
Tone down legal jargon in section 3 | Whitepaper | Kestrel thought leadership content | Kestrel Legal LLP | 2026-10-10 | 1 | 2 | Within limit | In scope | In progress | Pending |  | Sarah Chen
Replace stock photo in article 2 | Blog articles (x4) | Kestrel thought leadership content | Kestrel Legal LLP | 2026-09-24 | 1 | 1 | Last round | In scope | Resolved | Approved | 2026-09-29 | Sarah Chen
Add gluten-free icons to menu | Menu design | Pinecrest menu and signage | Pinecrest Bakery | 2026-09-08 | 1 | 2 | Within limit | Reasonable revision | Resolved | Approved | 2026-09-10 | Tom Alvarez
Change signage font to match menu | Store signage | Pinecrest menu and signage | Pinecrest Bakery | 2026-09-22 | 1 | 2 | Within limit | In scope | Resolved | Approved | 2026-09-25 | Tom Alvarez
Add allergen filters to menu | Ordering site design | Bluefin online ordering site | Bluefin Seafood Market | 2026-10-11 | 1 | 2 | Within limit | Reasonable revision | In progress | Pending |  | Marcus Webb
Reorder catalogue sections by season | Winter catalogue | Summit Ridge winter catalogue | Summit Ridge Outfitters | 2026-10-04 | 1 | 2 | Within limit | In scope | Resolved | Approved | 2026-10-07 | Tom Alvarez
Replace three product shots | Winter catalogue | Summit Ridge winter catalogue | Summit Ridge Outfitters | 2026-10-09 | 2 | 2 | Last round | In scope | In progress | Pending |  | Tom Alvarez
Update shipping stats on slide 4 | Sales deck | Atlas Logistics sales deck | Atlas Logistics | 2026-09-28 | 1 | 2 | Within limit | In scope | Resolved | Approved | 2026-10-01 | Marcus Webb
Rebuild deck in client template | Sales deck | Atlas Logistics sales deck | Atlas Logistics | 2026-10-05 | 2 | 2 | Last round | New requirement | Quoted as extra | Pending |  | Marcus Webb
Add French version of deck | Sales deck | Atlas Logistics sales deck | Atlas Logistics | 2026-10-12 | 3 | 2 | Over limit | New requirement | Open | Pending |  | Marcus Webb
Make hop illustration larger | Can label designs | Riverstone label redesign | Riverstone Brewing | 2026-10-03 | 1 | 2 | Within limit | In scope | Resolved | Approved | 2026-10-06 | Priya Nair
Change ABV font weight | Can label designs | Riverstone label redesign | Riverstone Brewing | 2026-10-07 | 2 | 2 | Last round | In scope | Resolved | Approved | 2026-10-08 | Priya Nair
Add enquiry form to project pages | Portfolio site design | Greenleaf portfolio site | Greenleaf Architects | 2026-09-10 | 1 | 2 | Within limit | Needs clarification | Open | Pending |  | Sarah Chen
Add room upgrade step to booking | Booking flow redesign | Cedar Grove booking flow refresh | Cedar Grove Hotel | 2026-08-18 | 1 | 2 | Within limit | Reasonable revision | Resolved | Approved | 2026-08-21 | Tom Alvarez

## Client health check scorecard
Client health check scorecard
Assess satisfaction, communication quality, delivery risk and renewal likelihood for each client.
Healthy |  | Watch |  |  | At risk |  |  | Average score out of 20
7 |  | 8 |  |  | 3 |  |  | 14.3
How to use
1. Read the scoring guide first, then add one row per client in the scorecard table below it. 2. Score each of the four criteria from 1 to 5, where 5 is the best outcome. 3. The total is out of 20 and is calculated, with the health label. Do not type over them. 4. Health label: 16 to 20 is Healthy, 11 to 15 is Watch, and 10 or less is At risk. A score of 2 sits between the Score 1 and Score 3 descriptions, and a score of 4 sits between Score 3 and Score 5. 5. Run the check on a regular schedule and plan an action for every client labelled Watch or At risk.
Scoring guide
Criterion |  |  | Score 1 |  |  | Score 3 |  | Score 5
Satisfaction |  |  | Client is openly unhappy |  |  | Client is neutral |  | Client is clearly pleased
Communication quality |  |  | Replies are rare or slow |  |  | Replies are steady but late at times |  | Replies are fast and clear
Delivery risk |  |  | Deadlines are missed or at serious risk |  |  | Some items are at risk |  | Delivery is on track
Renewal likelihood |  |  | Unlikely to continue |  |  | Undecided |  | Very likely to continue
Client name | Owner | Check date | Satisfaction | Communication quality | Delivery risk | Renewal likelihood | Total score | Health label | Next step
Northwind Coffee Co. | Sarah Chen | 2026-10-09 | 5 | 5 | 4 | 5 | 19 | Healthy | Propose 2027 retainer at renewal
Brightline Dental | Marcus Webb | 2026-10-09 | 4 | 3 | 3 | 4 | 14 | Watch | Unblock landing page before renewal talk
Halcyon Fitness | Priya Nair | 2026-10-09 | 2 | 2 | 1 | 2 | 7 | At risk | Escalation call to reset scope and timeline
Verdant Home Goods | Tom Alvarez | 2026-10-09 | 4 | 4 | 5 | 4 | 17 | Healthy | Keep onboarding on schedule
Kestrel Legal LLP | Sarah Chen | 2026-10-09 | 4 | 3 | 4 | 4 | 15 | Watch | Agree a faster approval route with partners
Oakridge Veterinary | Marcus Webb | 2026-10-09 | 3 | 2 | 2 | 2 | 9 | At risk | Confirm restart date or wind down
Lumen Solar | Priya Nair | 2026-10-09 | 4 | 3 | 5 | 3 | 15 | Watch | Build trust with strong logo concepts
Pinecrest Bakery | Tom Alvarez | 2026-10-09 | 4 | 4 | 5 | 1 | 14 | Watch | Deliver clean handover. Ask for a referral
Bluefin Seafood Market | Marcus Webb | 2026-10-09 | 4 | 4 | 4 | 5 | 17 | Healthy | Discuss phase 2 delivery app
Summit Ridge Outfitters | Tom Alvarez | 2026-10-09 | 3 | 3 | 2 | 3 | 11 | Watch | Recover catalogue timeline before renewal
Copperleaf Accounting | Sarah Chen | 2026-10-09 | 5 | 4 | 5 | 5 | 19 | Healthy | Pitch year-round content retainer
Meridian Physio | Priya Nair | 2026-10-09 | 4 | 4 | 5 | 4 | 17 | Healthy | Keep discovery on schedule
Atlas Logistics | Marcus Webb | 2026-10-09 | 2 | 2 | 2 | 2 | 8 | At risk | Reset scope with change request
Willow & Thread Boutique | Tom Alvarez | 2026-10-09 | 5 | 4 | 4 | 5 | 18 | Healthy | Ask for case study permission
Greenleaf Architects | Sarah Chen | 2026-10-09 | 3 | 2 | 3 | 3 | 11 | Watch | Clear photo rights to restart
Riverstone Brewing | Priya Nair | 2026-10-09 | 4 | 4 | 4 | 3 | 15 | Watch | Lock renewal after labels go to print
Nova Pet Supplies | Marcus Webb | 2026-10-09 | 4 | 4 | 5 | 4 | 17 | Healthy | Strong kickoff to build trust
Cedar Grove Hotel | Tom Alvarez | 2026-10-09 | 4 | 4 | 5 | 1 | 14 | Watch | Closed. Send survey and ask for a referral